## Cover Page
<Project Name>
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
Name
Role
Signature
Date
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog - Instructions C3: Protected Controlled Copy
Sprint Backlog
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
Sample
The sheet sample is an example sheet on how to fill the sprint backlog. Trainees can refer it to fill the details in the sheets Sprint 1/2/3.
Sprint 1/2/3
| User Story & Task Id | List the User Story id taken from product backlog that are selected to be completed in the particular sprint & List the number of tasks the User story is split into..
| Task | Name the tasks the user story is split into.
| Story Points | Enter the story points that was given for the user story during Sprint planning
| Assigned to | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5 | Task done in Day1/2/3/4/5 - Sprint review and retrospective to be held on Day 5
| Total | Summation of the estimation per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sample
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
USER STORY & TASK ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
US_1 | User Registration | 8
Task_1 | Create table to store registration details |  | Trainee_1 |  | 7 | 5 | 3 | 0 | 0 | 0
Task_2 | Design the registration page |  | Trainee_2 |  | 3 | 1 | 1 | 5 | 0 | 1
Task_3 | Design Login page |  | Trainee_1 |  | 1 | 0.5 | 0 | 3 | 0 | 0
Task_4 | Develop authentication process for login |  | Trainee_2 |  | 0.5 | 1 | 2 | 3 | 1 | 0
US_2 | Admin Home | 1
Task_1 | Create table to store Admin details |  | Trainee_3 |  | 3 | 3 | 0.5 | 0.5 | 0 | 0
Task_2 | Design the Admin registration page |  | Trainee_4 |  | 3 | 5 | 5 | 1 | 1 | 1
Task_3 | Develop code for authentication |  | Trainee_3 |  | 2 | 2 | 5 | 0 | 1 | 0
Task_4 | Develop code to store the admin details |  | Trainee_4 |  | 5 | 5 | 9 | 5 | 1 | 0
US_3 | Listing courses | 5
Task_1 | Develop code for Admin or vendor to add a course |  | Trainee_1 |  | 8 | 6 | 0 | 0 | 0 | 0
Task_2 | Develop Code ofr Admin or vendor to edit a course |  | Trainee_2 |  | 3 | 1 | 3 | 3 | 3 | 0
Task_3 | Develop code for - On clicking on edit a form should be pop up With valid input clicking on Add/update will update the database |  | Trainee_3 |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1
Task_4 | Develop code for Admin or vendor to activate or deactivate a course |  | Trainee_4 |  | 2 | 0.5 | 0 | 0 | 0 | 0
US_4 |  | 8
Task_1 |  |  |  |  | 9 | 4 | 2 | 2 | 1 | 1
Task_2 |  |  |  |  | 6 | 6 | 3 | 3 | 3 | 1
Task_3 |  |  |  |  | 6 | 2 | 8 | 8 | 1 | 0
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
US_5 |  | 3
Task_1 |  |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1
Task_2 |  |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9
Task_3 |  |  |  |  | 9 | 9 | 9 | 4 | 3 | 3
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0
TOTAL |  |  |  |  | 78 | 60 | 59 | 41 | 20 | 18

## Sprint -1
Sprint Backlog <Library Management System> Project ID: <MDU22AJ001/A054> C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1 | User/ Librarian/ Registration
Task_1 | Create table to store registration details |  | Abhishek
Task_2 | Design the registration page |  | Naman,Anuj
Task_3 | Design Login page |  | Ashutosh,Anuj
Task_4 | Develop authentication process for login |  | Shubham,Naman
User Story #2 | User Authentication
Task_1 | Create table to store user, librarian details |  | Ashutosh,Anuj
Task_2 | Design the user,librarian registration page |  | Abhishek
Task_3 | Develop code for authentication |  | Naman
Task_4 | Develop code to store the user details |  | Shubham
User Story #3 | Admin Credentials
Task_1 | Develop code for Admin or user |  | Abhishek
Task_2 | Develop Code of Admin or user |  | Anuj,Naman
Task_3 | Developing code |  | Ashutosh
Task_4 | Develop code for Admin or user |  | Shubham
User Story #4 | View Labrarian Details
Task_1 | Develop code for Admin to view Librarian Details |  | Shubham
Task_2 | Develop code to display librarian ID |  | Abhishek
Task_3 | Develop code to display librarian name |  | Ashutosh Anuj
Task_4 | Develop code to display librarian Email. ID |  | Naman Anuj
User Story #5 | Librarian Registration
Task_1 | Devolop code for admin to view new librarian registration |  | Naman
Task_2 | devolop code for admin to approve/reject the registration request |  | Anuj
Task_3 | devolop code to get message "Registration Rejected" on, rejection |  | Abhishek
Task_4 | Devolop code for librarian to log in successfully on approval |  | Shuham Ashutosh
TOTAL |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0

## Sprint -2
Sprint Backlog <Library Management System> Project ID: <MDU22AJ001/A054> C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #6 | Update Librarian Details
Task_1 | Devolop code for librarian to update the librarian details |  | Abhishek
Task_2 | Devolop code for librarian to update details like library name, add etc |  | Anuj
Task_3 | Devolop code for librarian to validate details |  | Naman
Task_4 | Develop code to test these methods |  | Shubham Ashutosh
User Story #7 | Add Books
Task_1 | Develop code for librarian to redirect to add books details page |  | Anuj,Ashutosh
Task_2 | Develop code for librarian to add the books and the competency |  | Naman
Task_3 | Develop code to create book id , book no. etc |  | Abhishek Shubham
Task_4 | Develop code to test these methods |  | Ashutosh Shubham
User Story #8 | View Books
Task_1 | Develop code for admin to redirect to book details page |  | Abhishek
Task_2 | Develop code for admin to view the books availabilty |  | Anuj
Task_3 | Develop code for librarian to redirect to books details page |  | Naman
Task_4 | Develop code to test these methods |  | Ashutosh Shubham
User Story #9 | Update Books Details
Task_1 | Develop code for librarian to rediect to book issue page |  | Anuj
Task_2 | Develop code to auto populate email, book issue/return date |  | Naman , Anuj
Task_3 | Develop code for librarian to enter other necessary details |  | Abhishek
Task_4 | Develop code to test these methods |  | Shubham Ashutosh
User Story #10 | Issued Books
Task_1 | Develop code for librarian to redirect to book details page |  | Ashutosh,Anuj
Task_2 | Develop code for librarian to view the book details |  | Shubham ,Naman
Task_3 | Develop code for librarian to issue books |  | Abhishek, Shubham
Task_4 | Develop code to test these methods |  | Ashutosh Shubham
User Story #11 | Search Books
Task_1 | Develop Code for user to search books |  | Abhishek
Task_2 | Develop code for user to search based of author ,book name, subject etc. |  | Shubham, Anuj
Task_3 | Develop code for user to see the availability of books |  | Naman Ashutosh
Task_4 | Develop code to test these methods |  | Ashutosh Shubham
User Story #12 | User Norms
Task_1 | Develop code for librarian to add/ upadte/ delete dos list in the user norms page |  | Naman
Task_2 | Develop code for librarian to add/ upadte/ delete donts list in the user norms page |  | Abhishek, anuj
Task_3 | Develop Code for user to view the user norms page |  | Anuj Abhishek
Task_4 | Develop code to test these methods |  | Ashutosh,Shubham
User Story #13 | User Feedback
Task_1 | Develop Code for user to take the survey |  | Abhishek
Task_2 | Develop code for user to fill feedback and submit |  | Shubham, Anuj
Task_3 | Develop code for user to disable pop-up after receiving feedback |  | Naman Ashutosh
Task_4 | Develop code to test these methods |  | Ashutosh Shubham
User Story #14 | Add Feedback Form
Task_1 | Develop code for admin to redirect to feedback form |  | Ashutosh,Shubham
Task_2 | Develop code for admin to fill the ratings |  | Naman
Task_3 | Develop code for admin to mack modification in the feedback form |  | Abhishek Naman
Task_4 | Develop code to test these methods |  | Anuj Abhishek
User Story #15 | LOG OFF
Task_1 | Develop code for admin to disconnect on clicking log off |  | Naman
Task_2 | Develop code for user to disconnect on clicking log off |  | Abhishek, anuj
Task_3 | Develop code for librarian to disconnect on clicking log off |  | Anuj Abhishek
Task_4 | Develop code to test these methods |  | Ashutosh,Shubham
TOTAL |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0

## Sprint -3
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
Report Generation
Task_1 | Develop code for admin to redirect to library name list |  | Naman,Ashutosh
Task_2 | Develop code for admin to generate report of the books based on category, usage |  | Anuj
Task_3 | Develop code for admin to generate monthly report of the lend books |  | Shubham , Abhishek
Task_4 | Develop to test these methods |  | Ashutosh Shubham
User Story #12 | User Page
Task_1 | Develop code for user to see the books details he has lended on login |  | Naman, Anuj
Task_2 | Develop code for user to see the date of books return / lended |  | Abhshek
Task_3 | Develop code for user to view the history of all the books he has lended |  | Anuj, Shubham
Task_4 | Develop code to test these methods |  | Ashutosh ,Shubham
User Story #13 | Search Books
Task_1 | Develop Code for user to search books |  | Abhishek
Task_2 | Develop code for user to search based of author ,book name, subject etc. |  | Shubham, Anuj
Task_3 | Develop code for user to see the availability of books |  | Naman Ashutosh
Task_4 | Develop code to test these methods |  | Ashutosh Shubham
User Story #14 | Sort and Filter options
Task_1 | Develop code for user to have sort and filter option |  | Ashutosh,Shubham
Task_2 | develop code for user to have sort and filter option based on book category , rating etc |  | Naman
Task_3 | Develop code for user to view book availibility based on sort and filter option |  | Abhishek Naman
Task_4 | Develop code to test these methods |  | Anuj Abhishek
User Story #15 | User Norms
Task_1 | Develop code for librarian to add/ upadte/ delete dos list in the user norms page |  | Naman
Task_2 | Develop code for librarian to add/ upadte/ delete donts list in the user norms page |  | Abhishek, anuj
Task_3 | Develop Code for user to view the user norms page |  | Anuj Abhishek
Task_4 | Develop code to test these methods |  | Ashutosh,Shubham
TOTAL |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0

## Data (hidden)
In-Progress
Completed
N/A